## Version
Version | Date | Changes
v1.0 | 2024-09-27 | Removed hardcoded projectname and tasklist and owner name
v1.1 | 2024-09-30 | Simplified inputs for user for ProjectNmae,TaskLists,OwnerName

## Tasks
Sr.No | ProjectName | TaskListname | TaskName | TaskDescrption | Task type | TaskID(require only for subtask create) | AssigneeName | Estimation(hrs) | StartDatae(m-d-y) | Duedate(m-d-y) | Priority | Sprint | Tags | ProjectNames | AssigneNames | Chandrayan 3 TaskList | SW Automation Tool Dev | iCook(MPP)
1 | SW Automation Tool Dev | C3 Automation | Dummy55425 | Dummy45 descripation | Task |  | Chandrashekhar MH | 20 | 2024-07-10 | 2024-10-10 | Medium | S7-SW-24 |  | Chandrayan 3 | Srilakshminarayanan Gokul(SW) | Power calibration Analysis and Follow up tasks | Mpp Approval | bbb
[14 empty] | iCookMPP | Ashik S Manjunath | TPT -EPP-BPP Project Backlogs | Github admin settings | cccc
[14 empty] | SW Automation Tool Dev | Yogesh V | TPT -EPP-BPP Project Backlogs | C3_Branching | ddd
[14 empty] | Sun | Mahesh N | TPT -EPP-BPP Project Backlogs | C3 Automation | 669359000013720358,669359000013720262
[14 empty] | Everest(C2Gen2) | Balamurugan M | SW CTS Dev | System DB Info Front End
[15 empty] | Sivan Perumal Pitchaiah | Calibrator-Proto | SW Backlogs - Auto CI testing
[15 empty] | Pallavi M.H. | SW Calibration Tasks | Apply the CI testing scope and test coverage framework to all modules
[15 empty] | Taranga Naik | SW UI - Refactor | SW Backlogs - Auto CI testing
[15 empty] | Hemalatha | SW UI Backlogs | Zoho API Scripts
[15 empty] | Guruprasad Thyagaraja Charya | SW Integration tasks | Backlogs
[15 empty] | Manjunath(SW) | SW BE Development | General
[15 empty] | Balaji s.m | Spec Understanding | C3/C2 QA Automation Tasks
[15 empty] | Jitendra Prabhu L | General | C2V Automation tool
Harish R (SW-UI)
Mark steev N
Nithish Vishal
DEEPAK P
Sandeep Manojkumar
Chandrashekhar MH
JAVAKAR T
Karthick R
Somasundaram S
Sai Trinadh Pavuluri
Sudharsanan
Pranay Nagpure Dilip
Hari Sundar
Saksham (SW-UI)
Karmukilan KT
Madankumar K
Ramanaa S
Chandra Shekar R
Addanki Krishnaprasad

## UserGuid
User Guide for Task Creation via Excel in Zoho
Headers Explanation
|  |  | Field | Description | Example
|  |  | TaskName | (Mandatory) Enter the task name. | Task creation through Zoho automation tool
|  |  | TaskDescription | (Mandatory) Enter a brief task description. | Using API and Excel input...
|  |  | ProjectName | (Mandatory) Specify the project name. | Chandrayan 3
|  |  | TaskListname | (Mandatory) Specify the task list name. | Development Tasks
|  |  | TaskID | (Mandatory) Enter a unique task ID. | 12345657
|  |  | Ownername | (Mandatory) Specify the task owner. | Mahesh
|  |  | StartDate | (Optional) Enter the task start date (mm-dd-yyyy). | 09-26-2024
|  |  | Duedate | (Optional) Enter the task due date (mm-dd-yyyy). | 09-27-2024
|  |  | Priority | (Optional) Set the task priority (e.g., Medium, High,Low). | Medium
|  |  | Sprint | (Optional) Specify the sprint name. | S7-SW-24
|  |  | Tags | (Optional) Add any relevant tags. | TPR,C3,UI,TPT
Note
1 | Fields highlighted in red are mandatory and must be filled out to successfully create a task.1
2 | Fields highlighted in gray are optional and can be left blank if not applicable.